## Sheet1
SORT | Goal |  | Objective |  | Action |  | Responsible Parties | [7 empty] | WMP Schedule | Labor | Hours | Cost | Evaluation Mechanism |  |  | Comments
[7 empty] | County | Health Dept | WWS | SWM | PEP Committee | M&M Committee | BMP Committee | Phase II Permitee | [5 empty] | Included in SWPPI | Permitee Schedule City of Swartz Creek
1 | 1. | Protect public health | a. | Ordinance to have septic systems inspected at “time of sale”’ | 1. | Draft an ordinance requiring inspection of septic systems at time of property sale. (County Wide) |  | Y | Y |  |  |  | Y |  | S | E342C | 80-100 hours | $5,000 - $10,000 | Draft ordinance is produced and adopted by Committee | Y | W
2 |  |  |  |  | 2. | Develop fee structure options for septic ordinance. |  | Y | Y |  |  |  | Y |  | S | E342C | 80-200 hours | $5,000 - $10,000 | Document that outlines fee options and evaluates the practicality of each of them. Adoption of a funding options) | Y | W
3 |  |  |  |  | 3. | The County will adopt a new ordinance for septic inspection. Municipal Permitees will support the ordinance. | Y | [6 empty] | Y | S | E342C | 20-100 hours | Legal fees per community | Resolution to support county or local ordiance is adopted by council | Y | W | City of Swartz Creek is willing to support a county wide ordinance adopted & enforced by the County but is not willing to adopt & enforce our own ordinance.
4 |  |  |  |  | 4. | Responsible Permitees will make appropriate staff available to be trained on enforcement. |  | Y | [5 empty] | Y | S | E342C | 100-400 hours | $300-$2000 | Municipal staff to attend training. | Y | N/A | See above
5 |  |  |  |  | 5. | Enforcement of the new septic ordinance |  | Y | [5 empty] | Y | L |  | TBD | TBD | No. of Inspections. Long Term Failure Rate Trend. Improvement in water quality, especially in rural areas. | Y | N/A | See above
6 |  |  |  |  | 6. | Develop & implement septic system tracking program for evaluation purposes. |  | Y |  | Y |  |  |  | Y | L |  | TBD | TBD | No. of Inspections. Long Term Failure Rate Trend | Y | N/A | See above
7 |  |  | b. | Develop Educational Materials For Homeowners With Septic Systems to be Given at “Time of Sale”. Main Topic: Septic System Maintenance. Other Topics: Include Lawn Maintenance, Auto Care, Well Water, Household Hazardous Waste Disposal, and well protection. | 1. | Explore funding options. Potentially use advertising to fund costs. |  |  |  |  | Y |  |  |  | S |  | 40-200 hours of prioritizing and finding funding | $8,000+ | Memo on options Presentations to appropriate authorities Adoption of a funding option | Y | E
8 |  |  |  |  | 2. | Develop partnership with local organizations, such as real estate agents. to promote and distribute information on septic systems. |  |  |  | Y | Y |  |  |  | S |  | 50-100 hours | $1-$3 ea 500 - 1000 packets $500 - $3000 Total | Distribution channels are established and maintained. No. of packets distributed by partners. | Y | 2012-04-01
9 |  |  |  |  | 3. | Implement distribution of booklet for new homeowners with septic systems. | [7 empty] | Y | S |  | 20-50 hours to distribute | TBD, dependent on distribution method | Count # packets distributed by Permitee to new home owners. | Y | 2012-04-01
10 |  |  |  |  | 4. | Develop tracking mechanism for evaluation purposes. |  |  |  |  | Y |  |  |  | S |  | 120 hours of organizing mailing | Brochures $2000-$10,000 | No. of packets printed and distributed by Permitees and organization. Social Survey | Y | 2012-04-01
29 | 2. | Establish a watershed stewardship ethic among the public | a. | Educate the public about the 7 required education elements | 1. | Update www.ClearGeneseeWater.org with watershed wide educational material, monitoring results, permit information, meeting information and committees as needed. |  |  |  |  | Y |  |  |  | O | E342C | 80-200 hours/year | Part of Education Media Campaign budget | No. of hits on website and downloads. List of information kept on website. | Y | E
30 |  |  |  |  | 2. | Place link on website connecting to above website if available. | [7 empty] | Y | S |  | Varies | Varies | Counters recording number of hits on Permitees websites | Y | E
31 |  |  |  |  | 3. | Develop print media to educate public. |  |  |  |  | Y |  |  |  | C | E342C | 60 hours | $2,000-$5,000 | Print material developed | Y | E
32 |  |  |  |  | 4. | Distribute media through municipalities. |  |  |  | Y |  |  |  | Y | O | E342C | 20 hours/year | Public education budget | No. of ad’s, print material and units distributed (etc.) by each Permitee | Y | E | Curently Distribute informational packets developed by PEP
33 |  |  |  |  | 5. | Develop evaluation method to track effectiveness of media. |  |  |  |  | Y |  |  |  | S |  | 200+hours | $3,000+ | No. of ad’s, print material and units distributed (etc.) by each Permitee Social survey | Y | E
34 |  |  | b. | Direct Mailing to Riparian Land owners (Rivers/Lakes) | 1. | Design riparian landowner educational materials emphasizing protecting and managing the riparian corridor. |  |  |  |  | Y |  |  |  | S |  | 80+ hours | Brochures part of Education Media Campaign budget $2,000-$10,000 | Creation of riparian landowner brochure. | Y | E | Currently evaluating whether to mail information and are exploring alternative options for program.
35 |  |  |  |  | 2. | Develop & maintain a list of riparian landowners. |  |  |  |  | Y |  |  |  | S |  | 20 hours per community | Develop cost analysis | List developed with regularly scheduled updates (5 yrs) | Y | E | List has been created.
36 |  |  |  |  | 3. | Implement direct mailings to land owners and updating public education materials. |  |  |  |  | Y |  |  |  | S |  | 30+ hours | $4,000-$8,000 | No. of information packets distributed No. of hits on web site. Returned postcard from newsletter | Y | E | Delivery vehicle is being determined.
37 |  |  |  |  | 4. | Develop evaluation method to track effectiveness of program. |  |  |  |  | Y |  |  |  | S |  | 200+hours | $3,000+ | No. of information packets distributed No. of hits on web site. Specific Survey. | Y | 2012-06-01 | Delivery vehicle is being determined.
42 |  |  | d. | Enhance Existing Benthic Monitoring Program | 1. | Meet with Flint River Watershed Coalition (FRWC) to identified opportunities to develop partnership(s). | [5 empty] | Y |  |  | C |  | 5 hours | Negligible | The 16 sites in Genesee county are tested consistently twice a year | Y | E
43 |  |  |  |  | 2. | Identify additional stream segments that would be desirable to gather macroinvertebrate sampling data on. | [5 empty] | Y |  |  | C |  | 10-20 hours | Negligible | Additional sites are identified. | Y | E
44 |  |  |  |  | 3. | Determine what additional resources are needed to expand the monitoring program. | [5 empty] | Y |  |  | O |  | 20 hours to meet to negotiate contract with FRWC | Negligible | Report of estimated additional resources needed. | Y | E
45 |  |  |  |  | 4. | Implement a yearly schedule and set up dead lines displaying when stream sections will be inventory yearly. |  |  | Y |  |  | Y |  |  | O | E342C contract done by FRWC | 10-20 hours | Part of below contract with FRWC | Schedule set | Y | E
46 |  |  |  |  | 5. | Sign contract with FRWC to provide Benthic Monitoring |  |  |  | Y |  | Y |  |  | C |  | Negligible | $5,150/year | Sign Contract | Y | E
47 |  |  |  |  | 6. | Review Results from past seasons. Current results will be reviewed each year after monitoring. |  |  |  | Y |  | Y |  |  | S | E342C | 40-80 hours/year | Negligible | Trend data is entered and analyzed. All monitoring activities should be related together (e.g. road/stream, WQ) | Y | E | Completed. See Project Green report in year end report.
48 |  |  |  |  | 7. | Conduct monitoring | [8 empty] | O | Done by FRWC | Part of below contract with FRWC | Part of below contract with FRWC | Track WQ improvements over the permit cycle | Y | E
49 |  |  | e. | Enhance Existing Project GREEN Program | 1. | Sign Contract with FRWC to administer program |  |  |  | Y |  | Y |  |  | C |  | Negligible | $7,500/year | Contract Signed | Y | E
50 |  |  |  |  | 2. | Identify local schools to participate. Meet with school district representatives | [5 empty] | Y |  |  | O | E342C | 40-80 hours/year | Done by contract with FRWC | Organizations that participate are identified. No. of classes participating in project Green. | Y | E
51 |  |  |  |  | 3. | Increase number of classes involved with program | [5 empty] | Y |  |  | O | Done by FRWC | Done by contract with FRWC | Done by contract with FRWC | Number of classes participating increase | Y | E
52 |  |  |  |  | 4. | Conduct monitoring | [5 empty] | Y |  |  | O | Done by FRWC | Done by contract with FRWC | Done by contract with FRWC | Samples of DO, Ammonia, Nitrate, PH, Phosphate, and temperature are collected regularly. Monitoring is completed and results are compiled | Y | E
53 |  |  |  |  | 5. | Review Results | [5 empty] | Y |  |  | S | E342C | 20 hours/month | Up to $5,000 | Results provided for all sites. Trend data is entered and analyzed | Y | E | See year end report.
54 |  |  | f. | Stream Crossing Watershed Survey with Photography. | 1. | Develop road stream inspection program. (Identify road/stream crossings, information collected) | [5 empty] | Y |  |  | C | E342C | 20 hours | Total additional cost $500-$2,000 | Documentation of water and stream characteristics, plant life, foam, trash, etc. | Y | E | Surveyed about 140 road/stream crossings with photos in 2007.
55 |  |  |  |  | 2. | Determine implementation options and responsibilities. | [5 empty] | Y |  |  | C | E342C | 20 hours | Negligible | Memo on options. Presentations to appropriate authorities | Y | E
56 |  |  |  |  | 3. | Provide training to personnel responsible for completing survey | [5 empty] | Y |  |  | O | E342C | 20 hours | $8,000/year | No. of people trained. Program sustained over time. | Y | E
57 |  |  |  |  | 4. | Conduct survey based on a schedule developed | [5 empty] | Y |  |  | S | E342C | 200+ hours per year | varies per year | Schedule is created and implemented. Photos are taken, reports are written | Y | E
58 |  |  |  |  | 5. | Review results |  |  |  | Y |  | Y |  |  | S | E342C | 20 hours | Negligible | Data entered and analysis performed. | Y | 2012-06-01
59 |  |  | g. | Hot Spot Water Quality Monitoring for MS4’s as needed | 1. | Identify initial list of target sites, chemical tests, parameters and collection method. | [5 empty] | Y |  |  | O | E342C | Will vary | Costs are as needed. Comes out of E342C | Documentation of water quality associated with hot spots. | Y | E | Through IDEP Program, hot spots have been identified for further investigation.
60 |  |  |  |  | 2. | Determine testing needed for each site. | [5 empty] | Y |  |  | C | E342C | Will vary | Will vary | Plan and needs assessment created. Advanced sample collection needs to be done by professionals | Y | E
61 |  |  |  |  | 3. | Create a protocol manual for fieldwork crews (lab results parameters and collection methods). | [5 empty] | Y |  |  | C | E342C | 10 hours | Costs are as needed. Comes out of E342C | Sites and protocols established | Y | E
62 |  |  |  |  | 4. | Schedule and conduct field work done by professionals (Consultants) | [5 empty] | Y |  |  | O | E342C | 80+ hours per year | $1,000-$1,500 per site | Schedule established, WQ samples collected | Y | E
63 |  |  |  |  | 5. | Review Results | [5 empty] | Y |  |  | O | E342C | 20 hours | Database costs are part of contract with Tetra Tech | Trend data is entered and analyzed. All monitoring activities should be related together (e.g. road/stream, WQ) | Y | E
64 | 3. | Reduce impact from peak flows | a. | Storm Water Ordinance | 1. | Create a storm water design standards/site plan manual. |  |  |  | y |  |  | Y |  | S | E342C | 200-2,000 hours |  | Creation of a design manual | Y | E
65 |  |  |  |  | 2. | Develop table that will show how much the installed BMPs will reduce or prevent post-construction impacts on water quality | [6 empty] | Y |  | L |  | Will vary for each Permitee | Will vary for each Permitee | Mechanism developed to track quantity and types of pollutants removed by various BMPs | Y | E
66 |  |  |  |  | 3. | Draft a stormwater ordinance that refers to the design/site plan manual that considers quantity and quality BMPs. | [6 empty] | Y |  | S | E342C | 40-200 hours per committee members | TBD | Draft ordinance is produced | Y | E
67 |  |  |  |  | 4. | Develop new County site plan review process with the following steps: Step 1: Pre-Development Step 2: Prepare site plan Step 3: Coordinated County Review Step 4: Municipal Review Step 5: Site Plan Step 6: Approval | [6 empty] | Y |  | L | E342C | 200+ | 5000 | Process is adopted and followed by county and communities. New development begins to take different form. | Y | E
68 |  |  |  |  | 5. | Develop permit fee structure to cover the cost of processing and enforcement with provision for future adjustments. | [6 empty] | Y |  | L | E342C | 20-100 hours | $2,500-$3,000 | Document that outlines fee options and evaluates the practicality of each of them. Adoption of a funding option(s) | Y | 2012-06-01
69 |  |  |  |  | 6. | Facilitate community acceptance through public forms and information packets. | [7 empty] | Y | L |  | 40-200 hours per community |  | Faclitate local Information sessions. No. of information packets distributed by Permitees | Y | 2011-2012
70 |  |  |  |  | 7. | Permitees to approve/adopt ordinance. | [7 empty] | Y | L |  | Will vary | Will vary | Resolution to support county or local ordiance is adopted by council | Y | 2012-06-01 | City has an existing storm water ordinance. They would be willing to look at the model ordinance to see if changes are needed
71 |  |  |  |  | 8. | Responsible Permitees will make appropriate staff available to be trained on the storm water ordinance, process and design manual. | [7 empty] | Y | L |  | 10 hours | 500 | Municipaly Staff will participate in training | Y | 2012
72 |  |  |  |  | 9. | SWM Permitees to enforce new storm water ordinance. | [7 empty] | Y | L |  | TBD | 3-4 staff $120-160K/year | No. of citations issued by Permitee No. of developments going thru the process. | Y | 2012+ | City of Swartz Creek already enforces the existing ordinance
91 | 4. | Create, restore, & Enhance Recreational Use | a. | Educate Public about recreational opportunities near/ on the water | 1. | Promote recreational programs (website, brochures, and community news.) | [7 empty] | Y | S |  | 10-20 Hours | 5000 | # of hits on Permitee's Parks and Recreation page (if applicable) Website. # of flyers distributed by Permitee. | Y | E
92 |  |  |  |  | 2. | Distribute materials on recreational programs through municipalities | [7 empty] | Y | S |  | 60-80 Hours | Nominal | # of hits on Permitee's Parks and Recreation page (if applicable) Website. # of flyers distributed by Permitee. | Y | E
97 | 5. | Restore and protect aquatic life, wildlife and habitat | a. | Establish vegetative buffer areas adjacent to sensitive areas | 1. | Draft Buffer Strip Ordinance | [6 empty] | Y |  | L | E342C | 100-500 hours | $5,000-$15,000 | Draft ordinance is produced | Y | 2013
98 |  |  |  |  | 2. | Develop fee structure options for buffer strip ordinance. | [6 empty] | Y |  | L | E342C | 100-500 hours | 5000 | Document that outlines fee options and evaluates the practicality of each of them. Adoption of a funding option(s)) | Y | 2013
99 |  |  |  |  | 3. | Permitees adopt new ordinance. | Y | [6 empty] | Y | L |  | 20-100 hours | Legal fees vary by community | Resolution to support local ordinance is adopted by council | Y | 2014 | City of Swartz Creek already has an exisitng set back ordinance. City is wiling to look at proposed ordinance for changes.
100 |  |  |  |  | 4. | Responsible Permitees will make appropriate staff available to be trained about the new buffer ordinance. | [7 empty] | Y | L |  | 10 hours per community | Staff costs vary by community | Municipal Staff to attend training | Y | 2014
101 |  |  |  |  | 5. | Permitees to enforce new stream buffer strip ordinance. | [7 empty] | Y | L |  | will vary by year | Enforcement costs will vary by community | No. of miles of buffer strips implemented. | Y | 2014 | City is currently enforcing setbacks through existing oridinance
102 |  |  |  |  | 6. | Develop tracking method for enforcement | [7 empty] | Y | L |  | TBD | TBD | No. of developments subject to new ordinance. | Y | 2014+ | City is currently tracking enforcement of existing oridinance
107 | 6. | MDEQ requirement - good housekeeping activities | a. | Ensure Maintenance activities, schedules, and inspection procedures for storm water structural controls (SWSC) as appropriate. | 1. | Develop or adopt a BMP manual to provide Permitees with maintenance procedures to be implemented for Good Housekeeping Activities | [7 empty] | Y | S |  | 20+ hours | nominal | BMP manual developed or adopted | Y | E
108 |  |  |  |  | 2. | Develop schedule for inspection & maintenance procedures of SWSC owned by Permitee | [7 empty] | Y | S |  | 60+ hours | nominal | Structural controls Identified. Maintenance and inspection schedule developed | Y | E
109 |  |  |  |  | 3. | Permitees will make appropriate staff available to be trained | [7 empty] | Y | S |  | 16+ hours per person | nominal | Appropriate municipal staff trained | Y | E | if contractors are used, Necessary language for training will be added to contract
110 |  |  |  |  | 4. | Inspect all SWSC owned by Permitee according to schedule | [7 empty] | Y | S |  | based on schedule developed | based on schedule developed | Inspections done according to schedule | Y | E
111 |  |  |  |  | 5. | Perform maintenance / repair to SWSC owned by Permitee (including but not limited to) | [7 empty] | Y | S |  | based on inspection made | based on inspection made | Maintenance of structural controls owned or operated by Permitee as needed according to inspection | Y | E | Maintenance is done on a as-needed based on Inspection
112 | [5 empty] | Pipes / culverts | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Pipes / culverts | Y | E
113 | [5 empty] | Ditches | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Ditches | Y | E
114 | [5 empty] | Catch Basins | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Catch Basins | Y | E
115 | [5 empty] | Oil-Grit Separators | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Oil-Grit Separators | Y | N/A | Does not have any
116 | [5 empty] | Detention (wet/dry) | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Detention (wet/dry) | Y | N/A | Does not have any
117 | [5 empty] | Vaults or tanks | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Vaults or tanks | Y | N/A | Does not have any
118 | [5 empty] | Infiltration Basin | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Infiltration Basin | Y | N/A | Does not have any
119 | [5 empty] | Rain Gardens | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Rain Gardens | Y | N/A | Does not have any
120 | [5 empty] | Porous Pavement | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Porous Pavement | Y | N/A | Does not have any
121 | [5 empty] | Vegetated Swales | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Vegetated Swales | Y | N/A | Does not have any
122 | [5 empty] | Constructed wetlands | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Constructed wetlands | Y | N/A | Does not have any
123 | [5 empty] | Filter Strips | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Filter Strips | Y | N/A | Does not have any
124 |  |  |  |  | 6. | Track inspection and maintenance | [7 empty] | Y | S |  | 200+ hours | nominal | Inspection findings recorded, maintenance performed Track quantity of pollutants removed or reduced. | Y | E
125 |  |  | b. | Implement Controls for reducing or eliminating the discharges of pollutants from streets, roads, highways, parking lots, and storage yards | 1. | Develop schedule & procedures for the following controls on pavement that is owned or operated by Permitee | [7 empty] | Y | S |  | 60+ hours | nominal | Schedule and O & M procedures developed | Y | E
126 | [5 empty] | Street Sweeping | [9 empty] | Per schedule | Vary by inspection | Vary by inspection | Street Sweeping | Y | E | Done by DPW
127 | [5 empty] | Road Salt Application & Storage | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Road Salt Application & Storage | Y | E | Done by DPW
128 | [5 empty] | Dust Control | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Dust Control | Y | E | only on park land
129 | [5 empty] | Snow Removal | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Snow Removal | Y | E | Done by DPW
130 | [5 empty] | Maintenance Garage / Storage Yards | [9 empty] | Per procedure | Vary by inspection | Vary by inspection | Maintenance Garage / Storage Yards | Y | E
131 | [5 empty] | Road & Bridge Maintenance | [9 empty] | Per schedule | Vary by inspection | Vary by inspection | Road & Bridge Maintenance | Y | E | Done through contract
132 | [5 empty] | Gravel Road Maintenance | [9 empty] | Per schedule | Vary by inspection | Vary by inspection | Gravel Road Maintenance | Y | E | 1 gravel road in park
133 | [5 empty] | Roadside Vegetation | [9 empty] | Per schedule | Vary by inspection | Vary by inspection | Roadside Vegetation | Y | E | Done by DPW
134 |  |  |  |  | 2. | Track inspection and maintenance of Controls | [7 empty] | Y | S |  | 200+ hours | nominal | Inspection findings recorded, maintenance performed. Track quantity of pollutants removed or reduced. | Y | E
135 |  |  | c. | Institute Procedures for the proper disposal of operation and maintenance waste from the separate storm water drainage system (from street sweeping, catch basin clean out, etc) | 1. | Develop procedure for proper disposal of the following waste collected from maintenance of the storm system owned or operated by Permitees | [7 empty] | Y | S |  | 60+ hours | nominal | Procedure developed and implemented | Y | E
136 | [5 empty] | Spoils / sediments | [10 empty] | Vary by year | Vary by year | Spoils / sediments | Y | E
137 | [5 empty] | Floatables / oil | [10 empty] | Vary by year | Vary by year | Floatables / oil | Y | E
138 | [5 empty] | Other Debris / Pollutants | [10 empty] | Vary by year | Vary by year | Other Debris / Pollutants | Y | E
139 |  |  |  |  | 2. | Document disposal method for operation and maintenance waste | [7 empty] | Y | S |  | 60+ hours | nominal | Track quantity of pollutants removed or reduced | Y | E
140 |  |  | d. | Ensure that flood management projects assess the impacts on the water quality of the receiving waters. | 1. | Evaluate current or create new procedures to place water quality measures on flood management projects owned by Permitee. | [7 empty] | Y | L |  | 200+ hours | nominal | Procedures for determining water quality measures has been evaluated / developed | Y | 2012
141 |  |  |  |  | 2. | Implement procedures on Permitee owned facilities | [7 empty] | Y | L |  | will vary based on procedures | no more than $2,000/year starting 2010 | Identified procedures implemented | Y | 2012 | City needed more time to enact implimentation
142 |  |  |  |  | 3. | Install BMPs where appropriate on Permitee owned facilities pursuant BMP manual | [7 empty] | Y | L |  | will vary based on procedures | no more than $2,000/year starting 2010 | Identified BMPs Installed | Y | 2012 | City needed more time to enact implimentation
143 |  |  |  |  | 4. | Assess new projects owned by Permitee for water quality impact. | [7 empty] | Y | L |  | Negligible | Negligible | Assessment done on site plan. Appropriate BMPs shown in design. | Y | 2013
144 |  |  | e. | Reduce the discharge of pollutants related to application of pesticides, herbicides, and fertilizers applied in the Permitees regulated area. | 1. | If fertilizers are used, Permitee will have soil testing performed, prior to application, and fertilizer application will be based on soil testing results. | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Fertilizer use policy changed if necessary | Y | N/A | Fertilizers are not used
145 |  |  |  |  | 2. | If fertilizers are used, Permitee will have fertilizer applied by a licensed individual | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Measure reduction or elimination of phosphorous and or fertilizer due to Permitee’s change in procedure. | Y | N/A | Fertilizers are not used
146 |  |  |  |  | 3. | If herbicides are used, Permitee will have herbicides applied by a licensed individual and the herbicides applied should be appropriate for use. | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Herbicide use policy changed if necessary. Reduce use of herbicide by Permitees | Y | N/A | Do not use Herbicides
147 |  |  |  |  | 4. | If pesticides are used outside, Permitee will apply sparingly by a licensed individual | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Pesticide use policy changed if necessary . Reduce use of pesticides by Permitees | Y | E | Pesticides are applied by a licenced individual.
148 |  |  |  |  | 5. | Pesticides, herbicides and fertilizers kept on site will be stored appropriately in dry, self contained areas that are not connected to the storm water drainage system. | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Procedures reviewed and adjusted if necessary. Material handling SOP adjusted | Y | N/A | City does not store fertilizers, pesticides or herbicides on property
149 | 7. | MDEQ requirement - post construction controls | a. | Evaluate and implement site appropriate, cost-effective structural and nonstructural best management practices (BMPs) that prevent or minimize post construction impacts on water quality. | 1. | Adopt BMPs manual from Objective 3a or develop and adopt a BMP manual to protect water quality in both new development and significant redevelopment | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Assessment is completed. BMP Manual created and adopted by Permitees. No. of people that use the manual. SOP are adjusted | Y | 2012
150 |  |  |  |  | 2. | Adopt the Objective 3a Stormwater ordinance to enforce BMP manual or develop and adopt individual Stormwater ordinance. | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | Necessary ordinances developed and adopted by Permitee | Y | 2012
151 |  |  |  |  | 3. | Responsible Permitees will make appropriate staff available to be trained on enforcement | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | Appropriate municipal staff trained | Y | 2012
152 |  |  |  |  | 4. | Develop & maintain tracking system | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | Mechanism developed to track number of sites, types of BMPs quantity of pollutants removed reduced | Y | 2012
[5 empty] | 5 | SWM Permitees to enforce new storm water ordinance. | [7 empty] | Y | L |  | TBD | 3-4 staff $120-160K/year | No. of citations issued by Permitee No. of developments going thru the process. | Y | 2012
153 |  |  | b. | Establish long-term operation and maintenance practices for storm water BMPs for new development and significant redevelopment on private property. | 1. | Review existing O&M practices as it relates to the adopted BMP manual. | [7 empty] | Y | S |  | Will vary for each Permitee | Will vary for each Permitee | Completion of review. Ability to determine needed O&M procedures | Y | 2012
154 |  |  |  |  | 2. | Develop a procedure to enforce new O & M practices on private storm water systems. | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | O&M procedures developed and supported by Permitee. | Y | 2012
155 |  |  |  |  | 3. | Adopt necessary ordinances to enforce new O & M practices on private storm water systems. | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | Necessary ordinances developed and adopted by Permitee. O&M manual/ procedures reflect new requirements | Y | 2012
156 |  |  |  |  | 4. | Responsible Permitees will make appropriate staff available to be trained on enforcement | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | appropriate municipal staff trained. | Y | 2012
157 |  |  |  |  | 5. | Develop & maintain tracking system | [7 empty] | Y | L |  | Will vary for each Permitee | Will vary for each Permitee | Mechanism developed to track number of sites, types of BMPs quantity of pollutants removed reduced | Y | 2013
[5 empty] | 6 | SWM Permitees to ensure O&M on post construction controls through the ordinance. | [7 empty] | Y | L |  | TBD | 3-4 staff $120-160K/year | No. of citations issued by Permitee No. of developments going thru the process. | Y | 2013 | Ordinance requires maintenance agreements on properties with new and significant redevelopment.
158 | 8. | Opportunities for sustainability | a. | Secure funding options available for implementation | 1. | Sign E342C contract (through May 1, 2008) | [7 empty] | Y | C |  |  |  | Permitee sign contract- see application | Y | E
159 |  |  |  |  | 2. | Review E342C contract for renewal | [7 empty] | Y | S |  | 30+ hours | 500 | Contract has been reviewed by Permitee | Y | 2013-03-01
160 |  |  |  |  | 3. | Sign new contract or develop funding mechanism to support independent program | [7 empty] | Y | S |  | nominal | nominal | Permitee either signs new contract based on new permit cycle or Permitee pursue implementation of permit with independent funding. | Y | 2013-03-01
163 |  |  | b. | Institutionalize the committee structure. | 1. | Phase II Permitee representative to sit on PE Committee. | [7 empty] | Y | O |  | 150+ hours per year | nominal | Attendance & Meeting Minutes. Action plan items are implemented. | Y | N/A | Each Community sits on 1 subcommittee. See MM Committtee
164 |  |  |  |  | 2. | Phase II Permitee representative to sit on BMP Committee. | [7 empty] | Y | O |  | 150+ hours per year | nominal | Attendance & Meeting Minutes. Action plan items are implemented. | Y | N/A | Each Community sits on 1 subcommittee. See MM Committtee
165 |  |  |  |  | 3. | Phase II Permitee representative to sit on MM Committee. | [7 empty] | Y | O |  | 150+ hours per year | nominal | Attendance & Meeting Minutes. Action plan items are implemented. | Y | E
166 |  |  |  |  | 4. | Phase II Permitee representative to sit on an Ad hoc Committee. | [7 empty] | Y | S |  | TBD | TBD | Attendance & Meeting Minutes. Action plan items are implemented. | Y | W